## Sqarime te pergjithshme
General explanations on Action Plan
These explanations are valid only for the phase of public consultation and after the aproval of this Action Plan extra detailed explanations will be attached | Ju lutem klikoni butonat në fund të kësaj faqeje për të hapur Planin e Veprimit, të ndarë sipas Objektivave Strategjike.
Terminology used and other explanations:
Timeline: Government strategy for cooperation with civil society covers a period of five years. This Action Plan is valid for first 3 years of the Strategy whereas detailed planning is done only for the first two years because at the end of the second years is planned a review of the Strategy and drafting of a new Action Plan. Understanding of timelines: With the letter Q is meant 'quarter year'. respectively three month period. Three month period starts from the moment of approval of the Strategy and this Action Plan. Separation into specific three month periods is done only for the first two years, respectively 8 three month periods in total. Financial cost: In the actual version. financial costs assigned for each specific activity are approximate costs. During the public consultation, Ministry of finance will calculate exact cost of each specific activity and will be attached in final version of this Action PlanGjatë kohëzgjatjes së konsultimit publik, Ministria e Financave do të llogarisë kost. Sources of Financing: Sources of financing in general will be provided by the budget of Republic of Kosovo. However, coordination unit for implementation of the Strategy will aim that for a number of specific activities to ensure financial support by different interested donors.

## Pjesemarrja qytetare
Activity | Responsible institution | Supporting institutions | Success indicators | Deadline for execution | Level of viability (A, B, C, D or E) | Comments | Financial cost and source of finance
Activities that concretise objectives of the Administration Reform Strategy and decompose relevant activities | Responsible institution/s for implementation of certain activity |  | Indicators serving for verification of activitiy execution | Deadline foreseen for complete execution of certain activity | Progress measures, which are: A – in total; B – majority of it; C – partly; E – none. | Eventual comments for activity or challenges faced during the implementation of activity | Presents the necessary budget for execution of relevant activity and the source of budget from which the activityi s planned to be financed.
Strategic objective: 1. Ensured and empowered participation of civil society in drafting and implementing of policies and legislation
Measure/Strategic sub-objective: 1.1. Drafting/amending-suplementing of basic legislation/reference for inclusion of CSO-s in drafting and implementing of policies
Measure indicator: 1.1. basic legislation for inclusion of CSO-s in drafting and implementing the policies is drafted
1.1.1. Identification of relevant legislation for drafting/amending-supplementing | OPM (Legal Office) | Line Ministries; CSO-s; other competent institutions | 1.1.1. Relevant legislation for amending-suplementing is identified | Q4 |  |  | 10,000 EUR
1.1.2. Drafting of identified normative acts | Line Ministires, other competent institutions | OPM (Legal Office); CSO-s; | 1.1.2. By-laws for implementation of lefislation in force are drafted | Q8 |  |  | 10,000 EUR
Measure/Strategic sub-objective: 1.2. defining the standards for inclusion of CSO-s in drafting and implementing of policies and legislation
Measure indicator: 1.2. minimal standards for inclusion of CSO-s are defined
1.2.1. Establishing platform/database which ensures information on the profile of organizations of civil society based on their fileds of activitiy | OPM (Office on Good Governance) | OPM ( Legal office, Office on Strategic Planning, Administrative Office, Koordinating Secretariat of the Government); MAP (DRNOJQ); CSO-s; | 1.2.1. information on the organizations of civil society are ensured through surveing their fileds of activity | Q2 |  |  | 5,000 EUR
1.2.2. Defininf minimum standards for public consultations | OPM (legal office) | OPM (Office on good governance, Office on strategic planning, Coordination secretariat of the Government, Communication office); CSO-s; | 1.2.2. standards for consultation with civil society are defined | Q3 |  |  | 5,000 EUR
1.2.3. Approval of regulative act for minimal standards for public consultations | Opm (legal office) |  | 1.2.3. regulative acts for minimal standards of inclusion of CSO-s is approved | Q4 |  |  | 0 EUR
1.2.4. Promotion of relevant act for minimal standards of inclusion of CSO-s | OPM (Communication office); | OPM (legal office, office on good governance); CSO-s; | 1.2.4. Respective act for standards of inlusion of CSO is promoted | Q6 |  |  | 5,000 EUR
Measure/strategic sub-objective: 1.3. Building professional capacities for civil employees and members of CSO in drafting and implementing of policies and legislation
Measure indicator: 1.3. professional capacities of civil employees and members of CSO-s are built
1.3.1. Identification of needs for training of civil employees and CSO representatives | OPM office on good governance); CSO-s | OPM (legal office, office on strategic planning); MPA (department of civil service administration; IKAP); CSO-s; | 1.3.1. the needs for training of civil employees and CSO representatives are indetified | Q4 |  |  | 15,000 EUR
1.3.2. Drafting of programs for continuous training of civil employees and CSO | OPM (office on good governance); CSO-s | OPM (legal office, office on strategic planning); MPA (Department of civil service administration; IKAP);CSO-s; | 1.3.2. Programs for continuous training for civil employees and CSO-s have been identified | Q5 |  |  | 10,000 EUR
1.3.3. organizing trainings for civil employees and CSO representatives | MPA (IKAP); CSO-s | OPM (legal office, office on strategic planning, office on good governance); MPA (department of civil sercive administration); CSO-s | 1.3.3. Continuous trainings for civil employees and CSO representatives | 2014-2015 |  |  | 60,000 EUR
1.3.4. Drafting of information materials and media campaigns for awarnesess | OPM (office on good governance) | OPM (communication office); cso-S | 1.3.4. Information material has been drafted and media campaigns for awareness were undertken | Q6 |  |  | 5,000 EUR
Measure/Strategic Sub-objective: 1.4. Establishing dhe system for supervision and reporting for inclusion of CSO
Measure indicator: 1.4. Supervision and report system has been established
1.4.1. Establishing of mechanisms for supervision of implementation of standards for public consultations | OPM (office on good governance) | OPM (legal office, office on strategic planning, government coordination secretariat, communication office); CSO-s | 1.4.1. the mechanism for supervision of implementation of standards for public communication | Q4 |  | Human resources | 20,000 EUR
1.4.2 Supervision and continuous report of inclusion of CSO | Institution/s responsible for implementation of certain activity |  | 1.4.4. There is supervision and reporting of inclusion of CSO. Regular reports on inclusion of CSO have been drafted and published as well as consultations in drafting of policies and legislation | 2014-2015 |  |  | Administrative cots

## Kontraktimi i sherbimeve
Activity | Responsible institution | Supportive institutions | Success indicators | Deadline for execution | Level of viability (A, B, C, D or E) | Comments | Financial cost and source of finance
Activities that materialize objectives of the Strategy on Reform of Public Administration and analyze respective activities | Responsible institution/s for implementation of certain activity |  | Indicators serving for verification of activitiy execution | Deadline foreseen for complete execution of certain activity | Progress measures, which are: A – in total; B – majority of it; C – partly; E – none. | Eventual comments for activity or challenges faced during the implementation of activity | Presents the necessary budget for execution of relevant activity and the source of budget from which the activityi s planned to be financed.
Strategic Objective: 2. Established system of contracting public services for civil society organizations
Measure/Strategic sub-objective: 2.1. drafting of legal framework that regulates contracting procedures of public services by CSO and defines fields of contracting
Measure indicator: 2.1. Legal framework on regulation of contracting public services by CSO is drafted
2.1.1. Establishment of a joint group to establish contracting system of public services by CSO | OPM (office on good governance); Joint established group | KRPP Ministry of Finance, line Ministries, other responsible institutions; CSO-s | 2.2.1. Joint body for determining of standards and principles of contracting public services by CSO is established | Q2 |  |  | Administrative cost
2.1.2. Analyses of actual legal framewor for regulating procedures f contracting public services by CSO | OPM (legal office); joint established group | Line Ministries, other responsible institutions; CSO-s | 2.1.1. Actual legal framework for regulating contracting procedures of public services by CSO is analysed | Q4 |  |  | 10,000 EUR
2.1.3. Identification of fields that CSO can be contracted t provide public service | OPM (office on good governance); Joint established group | OPM (office on strategic planning); Line Ministries, other responsible institutions; CSO-s | 2.1.2. Field, in which CSO can be contracted to provide public services are identified | Q4 |  |  | 3,000 EUR
2.1.4. Identification of organizations that have expertise on providing certain services | OPM (office on good governance); Joint established group | Line Ministries, other responsible institutions; CSO-s | 2.1.3. Organizations that have expertise on providing certain services are identified | Q4 |  |  | 5,000 EUR
2.1.5. Drafting/supplementing-amending of legal framework related to providing public services by organizations of civil society | Line Ministries, other responsible institutions,joint established group | CSO | 2.1.4. Legal framework related to providing public services by organizations of civil society is drafted | Q8 |  | Including foreign expertise | 15,000 EUR
2.1.6. Drafting of a continuous training program of civil servants for contraction of public services by CSO | Ministry of Public Administration; Joint established Group | Miistry of Finance; Regulatory Commission of Public Prokurment; Line Ministires, other responsible institutions; CSO-s | 2.1.5.continuous training program of civil servants for contraction of public services by CSO is drafted | 2015 |  |  | 5,000 EUR
2.1.7. Cataloging of public services that ca be contracted by CSO | OPM (office on good governance); Joint established group | Line Ministries, other responsible institutions; CSO-s | 2.1.6. Public services that ca be contracted by CSO are cataloged | 2015 |  |  | 3,000 EUR
Measure/Strategic sub-objective: 2.2. Defining standards and principles of contracting public services by CSO
Measure indicator: 2.2. Standards and principles of contracting public services by CSO are defined
2.2.1. Defining standards for contracting services by CSO | Joint established group | KRPP Ministry of Finance, line Ministries, other responsible institutions; CSO-s | 2.2.1. Standards and principles for contracting services by CSO are defined | 2015 |  | Including foreign expertise | 10,000 EUR
2.2.2. Accreditation and licencing of CSO-s that can provide public services | Competent institutions |  | 2.2.2. CSO-s that can provide public services are accreditted and licenced | 2015 |  |  | Administrative cost
2.2.3. Drafting of a procurment manual explaing procedures of contracting public services | Regulatory Commission of Public Procurment | Line Ministries, other responsible institutions; CSO-s | 2.1.3.procurment manual explaing procedures of contracting public services is drafted | 2015 |  |  | 5,000 EUR
Measure/Strategic sub-objective: 2.3. Establishing joint mechanism for supervision of implemtation of standards for licencing and provision of services
Measure indicator: 2.3. Supervision system has been established
2.3.1 Institutions are to appoint joint commission with CSO for supervision of implementation of standards | OPM (office on good governance) | KRPP Ministry of Finance, line Ministries, other responsible institutions; CSO-s | 2.3.1 Joint commission with CSO for supervision of implementation of standards is appointed | 2015 |  |  | Administrative cost
2.3.2. Periodical reports are drafted and published on implementation of standards and principles of contracting public services by CSO | Joint Commission | OPM (office on good governance); KRPP, Ministry of Finance, line Ministries, other competent institutions; CSO-s | 2.3.2. Periodical reports on implementation of standards and principles of contracting public services by CSO are drafted and published | 2015 |  |  | Administrative cost

## Perkrahja financiare
Activity | Responsible institution | Supportive Institutions | Success indicators | Deadline for execution | Level of viability (A, B, C, D or E) | Comments | Financial cost and source of finance
Actions which specify the objectives of Public Administration Reform and which analysis relevant activities | Institution/s responsible/for implementationof specific action |  | Indicators that serve to verify the implementation of action | Estimated time to complete the implementation of specific action | Progress measures, which are: A – overall; B – greatly; C – partly; E – none. | Eventual comments for action or challenges that arise during implementation of the action | Presents the necessary budget for implementation of relevant action and the source of the budget financed by the action plan.
Strategic Objective: 3. Established system and defined criteria for financial support for CSOs
Measure/Strategic sub-objective: 3.1. Legislation reform to implement joint projects
Indicator measure 3.1. Legislation is drafted and adapted for financing projects implemented by CSOs
3.1.1. Analysis of existing legislation to implement joint projects | Ministry of Finance | KRPP; OPM (Legal Office); CSOs | 3.1.1. Existing legislation is analyzed for joint implementation of policies and projects | Q4 |  | Joint Implementation projects shall mean contracting of CSOs to implement parts / specific projects of Government program | 5,000 EUR
3.1.2. Adoption of legislation according to needs identified through analysis | Ministry of Finance | KRPP; OPM (Legal Office); Line Ministries; CSOs | 3.1.2. Legislation is adopted according to needs identified through analysis | Q8 |  |  | 10,000 EUR
Measure/Strategic sub-objective: 3.2. Creating supportive environment for philanthropy and sponsorship
Indicator measure: 3.2. A favourable environment and encouraging philanthropy and sponsorship has been created
3.2.1. Drafting and approval of Law on philanthropy and sponsorship | Ministry of Finance | OPM (Legal Office); Line Ministries; CSOs | 3.2.1. It is designed and approved Law on philanthropy and sponsorship has been drafted and approved | Q4 |  | General law, not limited to any particular sector | 10,000 EUR
3.2.2. Determination and harmonization of fiscal and customs facilities for philanthropists and sponsors | Ministry of Finance | OPM (Legal Office); Line Ministries; CSOs | 3.2.2. Fiscal and customs facilities for philanthropists and sponsors are defined | Q8 |  |  | 5,000 EUR
Measure/Strategic sub-objective: 3.3. Standardization of public benefit status
Indicator measure: 3.3. Public benefit status is adopted and standarized
3.3.1.Analysis of legislation and mechanisms of public benefit status | OPM (Office on Good Governance; Legal Office) | MPA (DRNOJQ);Ministry of Finance; CSOs | 3.3.1. Analysed legislation and mechanisms for public benefits | Q2 |  |  | Administrative cost
3.3.2. Completion and harmonization of legislation for public benefit status | MPA (DRNOJQ); OPM (Legal Office) | OPM (Office on Good Governance); Ministry of Finance; CSOs | 3.3.2. Completed and harmonized legislation for public benefit status | Q4 |  |  | 5,000 EUR
Measure/Strategic sub-objective: 3.4. Civil society involvement into donor coordination mechanisms
Indicator measure: 3.4. Civil society is involved into donor coordination mechanisms
3.4.3. Opening of donors existing mechanism and database for contributions and use by CSOs | Ministry of European Integration | OPM (Office on Good Governance); CSOs | 3.4.4. The donors database for input and use by CSOs is opened | Q2 |  |  | Administrative cost
Measure/Strategic sub-objective: 3.5. Defining the criteria for the award and implementation of grants from public funds
Indicator measure: 3.5. Grants from public funds shall be allocated and implemented based on predetermined criteria
3.5.1. Defining the model National Grants Scheme for Civil Society (NGS) (National Fund for Civil Society Development) | OPM (Office on Good Governance) | Ministry of Finance; OSHC-të | 3.5.1. The model of National Grants Scheme is defined | Q4 |  |  | 5,000 EUR
3.5.2. Defining financial sources of National Grants Scheme(NGS) | Ministry of Finance | OPM; CSOs | 3.5.2. Financial sources of National Grant Scheme are defined | Q7 |  |  | Administrative cost
3.5.3. Defining the criteria for awarding grants from National Grant Scheme(NGS) | OPM (Office on Good Governance); | Ministry of Finance; CSOs | 3.5.3. The criteria for awarding grants from public funds are defined | Q8 |  |  | Administrative cost
3.5.4. Drafting and approval of normative acts for National Grant Scheme(NGS) | OPM (Legal Office) | Ministry of Finance; OPM (Office on Good Governance); CSOs | 3.5.4. Normative act for National Grant Scheme has been drafted and approved | 2015 |  |  | 5,000 EUR
3.5.5. Inclusion of National Grants Scheme within the MTEF | Ministry of Finance | OPM (Office on Good Governance); CSOs | 3.5.5. State Grants Scheme is included in the MTEF | 2015 |  |  | Administrative cost
3.5.6. Establishment of National Grants Scheme and functioning of mechanism responsible for programming, distribution, management and monitoring of national grants scheme | OPM (Office on Good Governance) | OPM; Ministry of Finance; Other relevant Institutions; CSOs | 3.5.6. It was established and is functional the National Grants Scheme | 2015 |  |  | N/A
3.5.7. Publication of reports on beneficiary projects, CSOs beneficiary, and the results of projects | National Grant Scheme (NGS) | OPM (Office on Good Governance); Ministry of Finance; CSOs | 3.5.7. Reports of beneficial projects, CSOs beneficiary , and the results of projects are published | 2015 |  |  | N/A
3.5.8. Support projects / cofinancing of CSOs by certain percentage for EU civil society funding | OPM (Office on Good Governance); | Ministry of Finance; OSHC-të | 3.5.8. CSOs projects are supported by certain percentage | Q4 |  | Procedures and criteria for cofinancing to be in accoredance with EU requirements | N/A
Measure/Strategic sub-objective: 3.6. Defining the criteria for non-financial support of CSOs
Indikatori i masës: 3.6. Kriteret për përkrahjen jo financiare për OShC janë përcaktuar
3.6.1.Analysis of current legislation that regulates the method of non-financial support | OPM (Legal Office) | Line Ministries; CSOs | 3.6.1. The current legislation which regulates the method of non-financial support is analysed | Q6 |  |  | 5,000 EUR
3.6.2. Amendment and supplementation of legislative package for non-financial support of CSOs | OPM (Legal Office) | Line Ministries; CSOs | 3.6.2.Completed / supplemented legal package for non-financial support of CSOs | Q8 |  |  | 5,000 EUR

## Vullnetarizmi
Activity | Responsible institution | Supportive institutions | Success indicators | Deadline for execution | Level of viability (A, B, C, D or E) | Comments | Financial cost and source of finance
Activities that materialize objectives of the Strategy on Reform of Public Administration and analyze respective activities | Responsible institution/s for implementation of certain activity |  | Indicators serving for verification of activitiy execution | Deadline foreseen for complete execution of certain activity | Progress measures, which are: A – in total; B – majority of it; C – partly; E – none. | Eventual comments for activity or challenges faced during the implementation of activity | Paraqet buxhetin e nevojshëm për realizimin e veprimit përkatës dhe burimin e buxhetit nga planifikohet të financohet veprimi.
Strategic Objective: 4. Promotion of integrated approach in developing of volunteering
Measure/ Strategic sub-objective: 4.1. Identification of needs and profile of volunteering in Kosovo
Measure indicator: 4.1. Needs and profile of volunteering in Kosovo are identified
4.1.1.Identification of responsible stakeholders | OGG | MCYS;line Ministries; CSO-s | 4.1.1. Responsible stakeholders are identified and contacted | Q1 |  |  | Administrative cost
4.1.2. Establishment of intersectorial group for volunteering | OGG | All responsible stakeholders, including CSO | 4.1.2. Intersectorial group for volunteering is established | Q2 |  |  | Administrative cost
4.1.3.Analyzing the profile of volunteering n Kosovo | Established group |  | 4.1.3.The profile of volunteering n Kosovo is analyzed | Q4 |  |  | 10,000 EUR
4.1.4. Implementation of recommendations emerged from analyses | Established group | Responsible institutions | 4.1.4. Recommendations emerged from analyses are being implemented | Q5 |  |  | 10,000 EUR
Masa/Nënobjektivi Strategjik: 4.2. Ndërtimi i sistemit të mbikëqyrjes dhe i raportimit për vullnetarizëm
Indikatori i masës: 4.2. Është ndërtuar sistemi i mbikqyrjes dhe i raportimit
4.2.1. Establishment of mechanism for supervision of implementation of integrated approach on volunteering | OGG/OPM | Legal office, office on strategic planning, government coordination secretariat, office for public communication, CSO-s | 4.2.1. Mechanism for supervision of implementation of integrated approach on volunteering is established | Q5 |  |  | Administrative cost
4.2.2. Continuous supervision and reporting of implementation of integrated approach on volunteering | OGG/OPM | responsible institution/s for implementation of certain activity | 4.2.2. Supervision and reporting of inclusion of CSO exists. Regular reports are drafted and published on volunteering | 2014-2015 |  |  | Administrative cost