## Instructions
EJA Kosovo Phase II — ODG Call 2
Logical Framework — Template for Applicants
Mandatory annex of the application form
Purpose of this template
This logical framework is the structured plan for what your organization will achieve, do, and produce under the Organizational Development Grant.
Structure
The logframe has three levels:
• OUTCOME — the organizational change this grant contributes to.
• OUTPUTS — the new systems, capacities, or practices that will exist at the end of the grant. Two to four outputs.
• ACTIVITIES — what you will do under each output. Listed at activity level, not sub-task level.
How to complete this template
• Open the "Logframe" sheet. The template is pre-structured with one Outcome, three Output rows, and grouped Activity rows. Add or remove Activity rows as needed within each Output. Do not add additional Outcomes.
• For every Indicator at Output level, you must provide a Baseline value and a Target value. Baseline is the state of your organization today. Target is the state at the end of the grant.
• Indicators should be observable and verifiable. Avoid abstractions like "improved governance". A good indicator describes something an outside observer (auditor, evaluator) could see or count at endline.
another word for endline
• Assumptions and Risks at the bottom of each level identify the conditions outside your control that could affect achievement. Be honest about real risks.
How this connects to the Self-Assessment chapter
The Outcome should reflect the overall organizational change you committed to in the Self-Assessment Part C ("What will be different at the end of the grant"). Each Output should correspond to one of the priority focus domains you identified in Self-Assessment Part B. The Output indicators should track the maturity-level shift you committed to in Self-Assessment Part C — for example, if you committed to moving Financial Management from Developing to Functional, the Financial Management Output should have indicators that demonstrate that move.
A filled out example
The Example Logical Framework sheet shows a complete logframe for a hypothetical organization (Advocacy Initiative Peja) that has identified Programmatic Systems and Strategy (Domain 3) and Resource Diversification and Sustainability (Domain 5) as its two priority focus areas. Read it before completing your own.
Common mistakes to avoid
• Confusing Outputs with Activities. An Output is what exists when the grant ends. An Activity is what you do to make it exist. "A written financial policy is in place and applied" is an Output. "Conduct a workshop to draft the financial policy" is an Activity.
• Indicators that cannot be verified. Avoid wording like "increased capacity", "stronger governance", "improved sustainability". These are aspirations. An indicator must point to something an evaluator can confirm.
• Activities that are not in the budget. Every activity in the logframe must appear in the budget.
• Targets disconnected from your maturity rubric commitments. If you committed in the Self-Assessment to moving from Developing to Functional in Domain 3 (Programmatic Systems and Strategy), the Output indicators here should reflect that.

## ODG_Logical Framework
Logical Framework — Organizational Development Grant
Applicant: [Organization name]
Grant duration: [Months]
Level | Description | Indicator | Baseline | Target | Source of verification | Assumptions / Risks
OUTCOME | [Write down the organizational change this grant contributes to. Should align with the change described in Chapter 4 of the application form.] | [1–2 outcome-level indicators that capture the overall organizational change] | [State at start of the grant] | [State at end of the grant] | [How will this be evidenced] | [Conditions outside your control that affect achievement]
OUTPUT 1 | [List the new system, capacity, or practice that will exist at end of grant. Should correspond to your highest-priority focus area from Self-Assessment Part B.] | [List indicators that capture Output 1] | [Current state] | [State at end of the grant] | [Document, system, evidence] | [Output-level risks]
Activity 1.1 | [Describe Activity 1.1] | [Activity-level indicator] | — |  | [Activity report, deliverable]
Activity 1.2 | [Describe Activity 1.2] | [Activity-level indicator] | — |  | [Activity report, deliverable]
Activity 1.3 | [Describe Activity 1.3] | [Activity-level indicator] | — |  | [Activity report, deliverable]
OUTPUT 2 | [Name the second new system, capacity, or practice. Should correspond to your second-priority focus area.] | [List indicators that capture Output 2] | [Current state] | [State at end of the grant] | [Document, system, evidence] | [Output-level risks]
Activity 2.1 | [Describe Activity 2.1] | [Activity-level indicator] | — |  | [Activity report, deliverable]
Activity 2.2 | [Describe Activity 2.2] | [Activity-level indicator] | — |  | [Activity report, deliverable]
Activity 2.3 | [Describe Activity 2.3] | [Activity-level indicator] | — |  | [Activity report, deliverable]
OUTPUT 3 | [Optional. Name the third new system, capacity, or practice. Should correspond to your second-priority focus area.] | [List indicators that capture Output 3] | [Current state] | [State at end of the grant] | [Document, system, evidence] | [Output-level risks]
Activity 3.1 | [Describe Activity 3.1] | [Activity-level indicator] | — | [Completion / quantity] | [Activity report, deliverable]
Activity 3.2 | [Describe Activity 3.2] | [Activity-level indicator] | — | [Completion / quantity] | [Activity report, deliverable]
Activity 3.3 | [Describe Activity 3.3] | [Activity-level indicator] | — | [Completion / quantity] | [Activity report, deliverable]
Cross-cutting issues
Level | Description | Indicator | Baseline | Target (endline) | Source of verification
Gender mainstreaming | [How will the organizational systems being built embed gender considerations? E.g., a policy that requires gender-disaggregated reporting on training participants; a board renewal practice that targets gender balance.] | [How this is evidenced] | [Current] | [Endline] | [Document or practice]
Environmental considerations | [How will the organizational systems being built embed environmental considerations? E.g., a procurement policy that prioritizes lower-impact options] | [How this is evidenced] | [Current] | [Endline] | [Document or practice]
Human rights based approach | [How will the organizational systems being built embed human-rights considerations? E.g., a non-discrimination provision in HR processes; data protection practices.] | [How this is evidenced] | [Current] | [Endline] | [Document or practice]

## Example Logical Framework
Example Logical Framework for Hypothetical Organization 'Advocacy Initiative Peja - AIP'
This is an illustrative completed logframe for an organization that prioritized in Programmatic Systems and Strategy (Domain 3) and Resource Diversification and Sustainability (Domain 5) in its Self-Assessment, both rated Developing. Committed target: Functional in both by grant end.
Level | Statement / Description | Indicator | Baseline | Target (endline) | Source of verification | Assumptions / Risks
OUTCOME | AIP's programmatic work is guided by a documented strategic framework and supported by a diversified funding base, reducing dependence on a single donor and improving the organization's ability to plan and deliver multi-year advocacy cycles. | (i) AIP has an approved strategic plan covering at least 2 years, with documented annual operational planning. (ii) AIP's income includes at least two active donors by grant end, with no single donor accounting for more than 70% of annual income. | (i) No strategic plan; annual priorities set informally. (ii) 100% of income from one donor. | (i) Strategic plan (2026–2028) approved by board; 2027 operational plan derived from it. (ii) Two or more active donors; largest donor share ≤70% of 2027 projected income. | (i) Signed strategy document; board minutes; 2027 operational plan. (ii) 2027 budget; signed contracts or grant agreements. | Continued employment of Program Coordinator; donors remain accessible to smaller CSOs; AIP's advocacy position does not deter new funders.
OUTPUT 1 | AIP has a written strategic plan (2026–2028) and an annual operational planning process derived from it, approved by the board and used to guide program decisions. | 1.1 Strategic plan (2026–2028) approved by board, including theory of change, priority domains, and measurable objectives. 1.2 2027 annual operational plan derived from the strategic plan, with activities, responsibilities, and budget allocations. | 1.1 No strategic plan. 1.2 No operational plan; work planned ad hoc. | 1.1 Board approval Q3 2026. 1.2 Operational plan approved Q4 2026. | 1.1 Signed strategy; board minutes. 1.2 Operational plan document; sign-off. | Facilitation quality depends on external consultant; board engagement required for approval milestone.
Activity 1.1 | Conduct a strategic planning process with staff and board, facilitated by an external consultant. | Facilitated process completed; draft strategy produced. | — | Q3 2026 | Facilitation report; participant list; draft strategy.
Activity 1.2 | Present draft strategy to board for review and approval. | Board approves strategy at formal meeting. | — | Q3 2026 | Board minutes; signed strategy.
Activity 1.3 | Develop 2027 annual operational plan based on strategy, including activity calendar, responsibilities, and budget. | Operational plan produced and approved. | — | Q4 2026 | Operational plan document.
OUTPUT 2 | AIP has a donor mapping, a written resource mobilization plan, and at least one new funding relationship initiated during the grant period. | 2.1 Written resource mobilization plan (2 year) identifying target donors, funding gaps, and responsibilities. 2.2 At least one concept note or full application submitted to a new donor by grant end. | 2.1 No resource mobilization plan. 2.2 No outreach to new donors in past 24 months. | 2.1 Plan produced and in use by Q3 2027. 2.2 At least one submission to a new donor by Q2 2027. | 2.1 Resource mobilization plan. 2.2 Submitted concept note | Donor landscape is uncertain and competitive; new-donor outreach competes with existing grant delivery for staff time.
Activity 2.1 | Map active and prospective donors relevant to AIP's mandate (local governance, accountability, civic space). | Donor mapping spreadsheet with at least 10 identified donors. | — | Q3 2026 | Mapping document.
Activity 2.2 | Develop resource mobilization plan based on the mapping, including 2-year pipeline and responsibilities. | Plan drafted and approved by ED and board. | — | Q4 2026 | Resource mobilization plan.
Activity 2.3 | Identify and approach one or two priority donors; submit at least one concept note or letter of interest. | At least one concept note submitted. | — | Q2 2027 | Submitted document with date-stamped cover email or portal submission confirmation.
Cross-cutting issues
Level | Description | Indicator | Baseline | Target (endline) | Source of verification
Gender mainstreaming | The strategic plan includes a gender equality commitment and the resource mobilization plan explicitly targets donors with gender-responsive funding tracks. | Gender section in strategy; at least one targeted donor in mapping has gender criteria. | No gender provisions in planning documents. | Q3 2026 (strategy); Q4 2026 (RM plan). | Strategy document; mapping.
Environmental considerations | The operational planning annex includes a low-carbon events preference (virtual or local options prioritized for meetings and trainings). | Provision in operational plan. | No environmental criteria. | Q4 2026. | Operational plan.
Human rights based approach | The resource mobilization plan includes a donor independence clause: AIP will not accept funding whose conditions conflict with its advocacy independence or human rights principles. | Donor independence clause present in resource mobilization plan. | No documented donor vetting criteria. | Q4 2026. | RM plan.